## Plan Summary
HRM / HRIS BUILD PLAN - 27 AUGUST to 15 SEPTEMBER 2026
Prepared for Sohel, erp.com.bd ¦ 14 modules ¦ 7-person team ¦ 14 working days (Sun-Thu week)
1. PLAN AT A GLANCE
Window | Thursday 27 August 2026 to Tuesday 15 September 2026 (20 calendar days)
Working days | 14 working days - Sunday to Thursday; Friday & Saturday are non-working
Total tasks | 47 scheduled tasks across 8 tracks
Scope tiers | 31 Must / 13 Should / 3
Modules covered | 24 module / sub-module lines mapping all 14 requested areas
Delivery on 15 Sep | UAT-ready build of all 14 modules; Could-tier features delivered at core level only
2. WAVE STRUCTURE
Wave | Dates | Days | Focus
Wave 0 | 27-28 Aug (D1-D2) | 2 | Kick-off, scope freeze, ERD & schema freeze, environments, common framework, test strategy
Wave 1 | 30 Aug - 3 Sep (D2-D6) | 5 | Foundation: Admin/Config/Setup, approval workflow engine, Employee Master, payroll config, ATS
Wave 2 | 6 - 10 Sep (D7-D11) | 5 | Core operations: Attendance, Leave, Payroll run, Security & LOG, Promotion, Letters, Assets, Documents, Policy, Reports
Wave 3 | 13 - 15 Sep (D12-D14) | 3 | Completion & hardening: IOM, TADA, PF/Gratuity, Exit, Performance, ESS, end-to-end testing, UAT build
3. TEAM & TRACK OWNERSHIP (7 people)
Track | Role | Modules owned |  | Tasks
Tech Lead | Architect / Lead Dev | Architecture & ERD, Administration/Config/Setup, HR Policy, HR Reports & Analytics, integration & UAT build |  | 7
Dev 1 (Platform) | Full-stack | Common framework, HR Request & Approval engine, Security & Administration (User Control/LOG), ESS portal |  | 7
Dev 2 (Lifecycle) | Full-stack | Employee Management, Promotion & Increment, Employee Document Management, Exit / Separation |  | 5
Dev 3 (Time) | Backend | HR Calendar, Shift & Attendance Setup, Attendance Management, Leave & IOM Management |  | 6
Dev 4 (Payroll) | Backend | Payroll & Compensation, TA/DA Bill, Benefits (PF / Gratuity), final settlement |  | 7
Dev 5 (Talent) | Full-stack | Recruitment / ATS, HR Letters & Certificates, Asset Assignment, Training & Development, Performance Management |  | 6
QA / BA | QA & Business Analyst | Test strategy, test cases, module & regression cycles, end-to-end scenarios, UAT pack |  | 7
4. MILESTONE GATES
M1 | 2026-09-03 | Foundation Freeze | Admin/Config, Employee Master, Approval Engine & Payroll config demo-ready
M2 | 2026-09-08 | Payroll Dry-Run | First monthly payroll executed on live attendance/leave data
M3 | 2026-09-10 | Feature Complete (Must) | All Must-tier modules code-complete; feature freeze begins
M4 | 2026-09-14 | UAT Build Deployed | Regression cycle 2 pass rate >= 95%; UAT environment live
M5 | 2026-09-15 | Internal Demo & Go/No-Go | All 14 modules demonstrated; UAT hand-over pack signed
5. GROUND RULES & ASSUMPTIONS
- | Working week is Sunday to Thursday; Friday and Saturday are non-working. That gives 14 working days, not 20 - the plan is built on 14.
- | Team assumed: 1 Tech Lead + 5 developers + 1 QA/BA. Changing the head-count changes the parallelism and the plan must be re-baselined.
- | Scope tiers: Must = non-negotiable for 15 Sep. Should = delivered unless a Must-tier item is at risk. Could = core functionality only, advanced features go to Phase 2.
- | The approval workflow engine (module 6) is built first in Wave 1 because Leave, IOM, TADA, Letters, Assets, Promotion and Exit all consume it. Do not let it slip.
- | Payroll is the critical path: Config -> Employee Master -> Attendance -> Leave -> Payroll. Any slip on that chain is a slip on 15 Sep.
- | Feature freeze starts at milestone M3 (10 Sep). After that only P1/P2 defect fixes go into the build.
- | Statutory parameters (tax slabs, PF rate, gratuity formula, labour-law leave entitlement) must be confirmed in writing by 31 Aug and built as configurable values.
- | 15 Sep delivers a UAT-ready build with seeded data, not a production go-live. Plan UAT, data migration and cut-over as a separate phase.
- | Each track holds a 15-minute stand-up at 09:30 and updates the Status column in the Task Detail sheet daily.

## Gantt
GANTT CHART - 27 AUG to 15 SEP 2026
Colour = owner track. Grey columns are the Friday/Saturday weekend. Diamond row marks milestones.
ID | Task | Module | Tier | 27 Aug | 28 Aug | 29 Aug | 30 Aug | 31 Aug | 01 Sep | 02 Sep | 03 Sep | 04 Sep | 05 Sep | 06 Sep | 07 Sep | 08 Sep | 09 Sep | 10 Sep | 11 Sep | 12 Sep | 13 Sep | 14 Sep | 15 Sep
|  |  | Day | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu
All
T01 | Kick-off, scope freeze & sign-off of all 14 modules | 0. Project Setup | Day: Must
T47 | Defect fix window - all tracks (P1/P2 only, feature freeze in force) | 0. Project Setup | Day: Must
Tech Lead
T02 | Master ERD & database schema freeze (all modules) | 0. Project Setup | Day: Must
T06 | Organisation Setup - company, branch, division, department, section, locati... | 1. Admin / Config / Setup | Day: Must
T07 | Job Structure - grade, designation, job role, job description, reporting hi... | 1. Admin / Config / Setup | Day: Must
T08 | Employee Configuration - employee type/category, confirmation rule, ID poli... | 1. Admin / Config / Setup | Day: Must
T25 | HR Policy Management - policy library, versioning, publish & acknowledgemen... | 2. HRIS Operation | Day: Should
T26 | HR Reports & Analytics - reporting framework, HR dashboard, standard report... | 2. HRIS Operation | Day: Should
T46 | Integration, code review, performance tuning, UAT build deployment | 0. Project Setup | Day: Must
Dev 1 (Platform)
T03 | Dev/Test environment, repository, CI pipeline, coding standards | 0. Project Setup | Day: Must
T04 | Common framework: audit stamp, auto-numbering, notification, file store | 0. Project Setup | Day: Must
T11 | Generic approval workflow engine - multi-level, delegation, escalation, SLA | 6. HR Request & Approval | Day: Must
T12 | Request catalogue, approval inbox/outbox, e-mail & in-app notification | 6. HR Request & Approval | Day: Must
T27 | Role / User / Employee access management, menu & field permission matrix | 14. Security & Administration | Day: Must
T28 | Audit log, user activity trail, login history, data-change history | 14. Security & Administration | Day: Must
T41 | ESS portal - profile, attendance, leave apply, payslip, requests, letters, ... | 12. Employee Self-Service | Day: Should
Dev 2 (Lifecycle)
T13 | Employee Management - core profile (personal, official, contact, family, ed... | 2. HRIS Operation | Day: Must
T14 | Employee Management - service book, transfer/posting, confirmation, bulk im... | 2. HRIS Operation | Day: Must
T29 | Promotion & Increment - proposal, approval, effect on grade & payroll, history | 2. HRIS Operation | Day: Must
T30 | Document types, upload & versioning, expiry alerts, bulk upload, employee d... | 10. Employee Document Mgmt | Day: Should
T31 | Resignation, notice period, clearance checklist, exit interview, service ce... | 13. Employee Exit / Separation | Day: Should
Dev 3 (Time)
T09 | HR Calendar - holiday calendar, weekend policy, leave & fiscal year, event ... | 1. Admin / Config / Setup | Day: Must
T10 | Shift & Attendance Setup - shift master, roster pattern, grace/late rule, O... | 1. Admin / Config / Setup | Day: Must
T21 | Attendance Management - device sync, daily attendance, roster, OT, manual r... | 2. HRIS Operation | Day: Must
T22 | Leave & IOM - leave types, entitlement, accrual, application, approval, bal... | 2. HRIS Operation | Day: Must
T23 | Inter-Office Memo (IOM) - drafting, routing, acknowledgement, archive | 2. HRIS Operation | Day: Should
T24 | Attendance & leave reports (late/absent, OT register, leave ledger) | 2. HRIS Operation | Day: Should
Dev 4 (Payroll)
T15 | Salary structure, pay component & formula engine, grade-wise pay scale | 3. Payroll & Compensation | Day: Must
T16 | Employee salary assignment, arrear/adjustment setup, income tax & AIT confi... | 3. Payroll & Compensation | Day: Must
T32 | Monthly payroll processing - attendance & leave integration, arrear, deduct... | 3. Payroll & Compensation | Day: Must
T33 | Payslip, bank advice / disbursement file, payroll register, tax statement | 3. Payroll & Compensation | Day: Must
T34 | TA/DA Bill - travel request, bill entry, policy-based entitlement, approval... | 2. HRIS Operation | Day: Should
T35 | Provident Fund - contribution, ledger, interest, loan & withdrawal; Gratuit... | 5. Benefits (PF / Gratuity) | Day: Should
T36 | Final settlement - exit dues, gratuity, PF, leave encashment; payroll defec... | 5. Benefits (PF / Gratuity) | Day: Could
Dev 5 (Talent)
T17 | Manpower requisition & approval, job posting, career page | 4. Recruitment / ATS | Day: Should
T18 | Applicant pipeline, shortlist, interview schedule & scoring, offer, onboard... | 4. Recruitment / ATS | Day: Should
T37 | Letter templates, merge fields, auto-numbering, approval, PDF generation & ... | 7. HR Letters & Certificates | Day: Should
T38 | Asset register, issue / return / transfer, acknowledgement, employee-wise a... | 8. HR Asset Assignment | Day: Should
T39 | Training plan & calendar, nomination, attendance, evaluation, cost & effect... | 9. Training & Development | Day: Could
T40 | KPI / goal setting, appraisal cycle, self & manager review, rating, calibra... | 11. Performance Management | Day: Could
QA / BA
T05 | Test strategy & master test-case backlog | 0. Project Setup | Day: Must
T19 | Wave-1 test cases + seeded test data (org, jobs, employees) | QA | Day: Must
T20 | Test cycle - Organisation, Job Structure, HR Calendar, Shift Setup | QA | Day: Must
T42 | Test cycle - Employee Mgmt, Approval engine, Recruitment; defect logging | QA | Day: Must
T43 | Test cycle - Attendance, Payroll, Security, Letters, Promotion; regression ... | QA | Day: Must
T44 | End-to-end scenario test: hire - attendance - leave - payroll - exit; regre... | QA | Day: Must
T45 | UAT pack, demo script, release notes, go / no-go checklist | QA | Day: Must
| MILESTONES |  | Th: M1; Tu: M2; Th: M3; Mo: M4; Tu: M5

## Task Detail
TASK PLAN - HRM / HRIS BUILD (27 Aug - 15 Sep 2026)
Duration is calculated by formula from the Calendar sheet. Update the Status column as work progresses.
ID | Module | Task / Deliverable Scope | Owner (Track) | Start | Finish | Working Days | Depends On | Scope Tier | Output | Status
T01 | 0. Project Setup | Kick-off, scope freeze & sign-off of all 14 modules | All | 2026-08-27 | 2026-08-27 | 1 | - | Must | Signed scope baseline | Not started
T02 | 0. Project Setup | Master ERD & database schema freeze (all modules) | Tech Lead | 2026-08-27 | 2026-08-30 | 2 | T01 | Must | ERD + migration scripts | Not started
T03 | 0. Project Setup | Dev/Test environment, repository, CI pipeline, coding standards | Dev 1 (Platform) | 2026-08-27 | 2026-08-27 | 1 | - | Must | Environments live | Not started
T04 | 0. Project Setup | Common framework: audit stamp, auto-numbering, notification, file store | Dev 1 (Platform) | 2026-08-30 | 2026-08-30 | 1 | T02 | Must | Shared libraries | Not started
T05 | 0. Project Setup | Test strategy & master test-case backlog | QA / BA | 2026-08-27 | 2026-08-30 | 2 | T01 | Must | Test plan v1.0 | Not started
T06 | 1. Admin / Config / Setup | Organisation Setup - company, branch, division, department, section, location, cost centre | Tech Lead | 2026-08-30 | 2026-08-31 | 2 | T02 | Must | Org master screens | Not started
T07 | 1. Admin / Config / Setup | Job Structure - grade, designation, job role, job description, reporting hierarchy | Tech Lead | 2026-09-01 | 2026-09-02 | 2 | T06 | Must | Job structure module | Not started
T08 | 1. Admin / Config / Setup | Employee Configuration - employee type/category, confirmation rule, ID policy, custom fields | Tech Lead | 2026-09-03 | 2026-09-03 | 1 | T07 | Must | Employee config module | Not started
T09 | 1. Admin / Config / Setup | HR Calendar - holiday calendar, weekend policy, leave & fiscal year, event calendar | Dev 3 (Time) | 2026-08-30 | 2026-08-31 | 2 | T02 | Must | HR calendar module | Not started
T10 | 1. Admin / Config / Setup | Shift & Attendance Setup - shift master, roster pattern, grace/late rule, OT rule, device mapping | Dev 3 (Time) | 2026-09-01 | 2026-09-02 | 2 | T09 | Must | Shift setup module | Not started
T11 | 6. HR Request & Approval | Generic approval workflow engine - multi-level, delegation, escalation, SLA | Dev 1 (Platform) | 2026-08-31 | 2026-09-02 | 3 | T04 | Must | Workflow engine | Not started
T12 | 6. HR Request & Approval | Request catalogue, approval inbox/outbox, e-mail & in-app notification | Dev 1 (Platform) | 2026-09-03 | 2026-09-03 | 1 | T11 | Must | Request & approval UI | Not started
T13 | 2. HRIS Operation | Employee Management - core profile (personal, official, contact, family, education, experience) | Dev 2 (Lifecycle) | 2026-08-30 | 2026-09-01 | 3 | T02 | Must | Employee master | Not started
T14 | 2. HRIS Operation | Employee Management - service book, transfer/posting, confirmation, bulk import | Dev 2 (Lifecycle) | 2026-09-02 | 2026-09-03 | 2 | T13,T08 | Must | Employee lifecycle screens | Not started
T15 | 3. Payroll & Compensation | Salary structure, pay component & formula engine, grade-wise pay scale | Dev 4 (Payroll) | 2026-08-30 | 2026-09-01 | 3 | T02 | Must | Payroll config | Not started
T16 | 3. Payroll & Compensation | Employee salary assignment, arrear/adjustment setup, income tax & AIT configuration | Dev 4 (Payroll) | 2026-09-02 | 2026-09-03 | 2 | T15,T13 | Must | Salary assignment | Not started
T17 | 4. Recruitment / ATS | Manpower requisition & approval, job posting, career page | Dev 5 (Talent) | 2026-08-30 | 2026-08-31 | 2 | T02,T07 | Should | Requisition & posting | Not started
T18 | 4. Recruitment / ATS | Applicant pipeline, shortlist, interview schedule & scoring, offer, onboarding hand-off | Dev 5 (Talent) | 2026-09-01 | 2026-09-03 | 3 | T17 | Should | ATS pipeline | Not started
T19 | QA | Wave-1 test cases + seeded test data (org, jobs, employees) | QA / BA | 2026-08-31 | 2026-09-01 | 2 | T05 | Must | Test cases + data set | Not started
T20 | QA | Test cycle - Organisation, Job Structure, HR Calendar, Shift Setup | QA / BA | 2026-09-02 | 2026-09-03 | 2 | T06,T07,T09,T10 | Must | Defect log W1 | Not started
T21 | 2. HRIS Operation | Attendance Management - device sync, daily attendance, roster, OT, manual regularisation | Dev 3 (Time) | 2026-09-03 | 2026-09-07 | 3 | T10 | Must | Attendance module | Not started
T22 | 2. HRIS Operation | Leave & IOM - leave types, entitlement, accrual, application, approval, balance, encashment | Dev 3 (Time) | 2026-09-08 | 2026-09-10 | 3 | T09,T11 | Must | Leave module | Not started
T23 | 2. HRIS Operation | Inter-Office Memo (IOM) - drafting, routing, acknowledgement, archive | Dev 3 (Time) | 2026-09-13 | 2026-09-13 | 1 | T11 | Should | IOM module | Not started
T24 | 2. HRIS Operation | Attendance & leave reports (late/absent, OT register, leave ledger) | Dev 3 (Time) | 2026-09-14 | 2026-09-14 | 1 | T21,T22 | Should | Report pack | Not started
T25 | 2. HRIS Operation | HR Policy Management - policy library, versioning, publish & acknowledgement tracking | Tech Lead | 2026-09-06 | 2026-09-07 | 2 | T04 | Should | Policy module | Not started
T26 | 2. HRIS Operation | HR Reports & Analytics - reporting framework, HR dashboard, standard report pack, export | Tech Lead | 2026-09-08 | 2026-09-10 | 3 | T14,T21 | Should | Dashboard + reports | Not started
T27 | 14. Security & Administration | Role / User / Employee access management, menu & field permission matrix | Dev 1 (Platform) | 2026-09-06 | 2026-09-08 | 3 | T12 | Must | RBAC module | Not started
T28 | 14. Security & Administration | Audit log, user activity trail, login history, data-change history | Dev 1 (Platform) | 2026-09-09 | 2026-09-09 | 1 | T27 | Must | Audit & LOG | Not started
T29 | 2. HRIS Operation | Promotion & Increment - proposal, approval, effect on grade & payroll, history | Dev 2 (Lifecycle) | 2026-09-06 | 2026-09-07 | 2 | T14,T07 | Must | Promotion module | Not started
T30 | 10. Employee Document Mgmt | Document types, upload & versioning, expiry alerts, bulk upload, employee dossier | Dev 2 (Lifecycle) | 2026-09-08 | 2026-09-09 | 2 | T14 | Should | Document module | Not started
T31 | 13. Employee Exit / Separation | Resignation, notice period, clearance checklist, exit interview, service certificate trigger | Dev 2 (Lifecycle) | 2026-09-10 | 2026-09-13 | 2 | T14,T11 | Should | Exit module | Not started
T32 | 3. Payroll & Compensation | Monthly payroll processing - attendance & leave integration, arrear, deduction, hold/release | Dev 4 (Payroll) | 2026-09-06 | 2026-09-08 | 3 | T16,T21 | Must | Payroll run | Not started
T33 | 3. Payroll & Compensation | Payslip, bank advice / disbursement file, payroll register, tax statement | Dev 4 (Payroll) | 2026-09-09 | 2026-09-10 | 2 | T32 | Must | Payroll outputs | Not started
T34 | 2. HRIS Operation | TA/DA Bill - travel request, bill entry, policy-based entitlement, approval, payroll posting | Dev 4 (Payroll) | 2026-09-13 | 2026-09-13 | 1 | T11,T32 | Should | TADA module | Not started
T35 | 5. Benefits (PF / Gratuity) | Provident Fund - contribution, ledger, interest, loan & withdrawal; Gratuity accrual & calculation | Dev 4 (Payroll) | 2026-09-14 | 2026-09-14 | 1 | T32 | Should | PF & gratuity | Not started
T36 | 5. Benefits (PF / Gratuity) | Final settlement - exit dues, gratuity, PF, leave encashment; payroll defect fixes | Dev 4 (Payroll) | 2026-09-15 | 2026-09-15 | 1 | T31,T35 | Could | Final settlement | Not started
T37 | 7. HR Letters & Certificates | Letter templates, merge fields, auto-numbering, approval, PDF generation & register | Dev 5 (Talent) | 2026-09-06 | 2026-09-07 | 2 | T14,T11 | Should | Letter module | Not started
T38 | 8. HR Asset Assignment | Asset register, issue / return / transfer, acknowledgement, employee-wise asset ledger | Dev 5 (Talent) | 2026-09-08 | 2026-09-08 | 1 | T14 | Should | Asset module | Not started
T39 | 9. Training & Development | Training plan & calendar, nomination, attendance, evaluation, cost & effectiveness tracking | Dev 5 (Talent) | 2026-09-09 | 2026-09-10 | 2 | T14 | Could | Training module | Not started
T40 | 11. Performance Management | KPI / goal setting, appraisal cycle, self & manager review, rating, calibration, PIP | Dev 5 (Talent) | 2026-09-13 | 2026-09-14 | 2 | T07,T14 | Could | Appraisal module | Not started
T41 | 12. Employee Self-Service | ESS portal - profile, attendance, leave apply, payslip, requests, letters, document view | Dev 1 (Platform) | 2026-09-10 | 2026-09-14 | 3 | T22,T33,T27 | Should | ESS portal | Not started
T42 | QA | Test cycle - Employee Mgmt, Approval engine, Recruitment; defect logging | QA / BA | 2026-09-06 | 2026-09-07 | 2 | T14,T12,T18 | Must | Defect log W2a | Not started
T43 | QA | Test cycle - Attendance, Payroll, Security, Letters, Promotion; regression cycle 1 | QA / BA | 2026-09-08 | 2026-09-10 | 3 | T21,T32,T27,T37,T29 | Must | Regression report 1 | Not started
T44 | QA | End-to-end scenario test: hire - attendance - leave - payroll - exit; regression cycle 2 | QA / BA | 2026-09-13 | 2026-09-14 | 2 | T33,T31,T41 | Must | Regression report 2 | Not started
T45 | QA | UAT pack, demo script, release notes, go / no-go checklist | QA / BA | 2026-09-15 | 2026-09-15 | 1 | T44 | Must | UAT hand-over pack | Not started
T46 | 0. Project Setup | Integration, code review, performance tuning, UAT build deployment | Tech Lead | 2026-09-13 | 2026-09-15 | 3 | All | Must | UAT build v1.0 | Not started
T47 | 0. Project Setup | Defect fix window - all tracks (P1/P2 only, feature freeze in force) | All | 2026-09-15 | 2026-09-15 | 1 | T44 | Must | Stabilised build | Not started

## Module Coverage
MODULE COVERAGE - ALL 14 AREAS
Every requested module mapped to its build tasks, owner, delivery date and scope tier.
# | Module / Sub-module | Scope delivered by 15 Sep | Owner | Tasks | Delivered by | Tier
1 | Administration / Config / Setup - Organisation Setup | Company, branch, division, department, section, location, cost centre masters | Tech Lead | T06 | 31-Aug (D3) | Must
1 | Administration / Config / Setup - Job Structure | Grade, designation, job role, job description, reporting hierarchy | Tech Lead | T07 | 02-Sep (D5) | Must
1 | Administration / Config / Setup - Employee Configuration | Employee type/category, confirmation rules, ID/code policy, custom fields | Tech Lead | T08 | 03-Sep (D6) | Must
1 | Administration / Config / Setup - HR Calendar | Holiday calendar, weekend policy, leave & fiscal year, event calendar | Dev 3 (Time) | T09 | 31-Aug (D3) | Must
1 | Administration / Config / Setup - Shift & Attendance Setup | Shift master, roster pattern, grace/late rules, OT rules, device mapping | Dev 3 (Time) | T10 | 02-Sep (D5) | Must
2 | HRIS Operation - Employee Management | Full profile, service book, transfer/posting, confirmation, bulk import | Dev 2 (Lifecycle) | T13, T14 | 03-Sep (D6) | Must
2 | HRIS Operation - Attendance Management | Device sync, daily attendance, roster, OT, manual regularisation, reports | Dev 3 (Time) | T21, T24 | 14-Sep (D13) | Must
2 | HRIS Operation - Leave & IOM Management | Leave types, entitlement, accrual, application/approval, balance, encashment; IOM routing | Dev 3 (Time) | T22, T23 | 13-Sep (D12) | Must
2 | HRIS Operation - TA/DA Bill | Travel request, bill entry, entitlement by grade, approval, posting to payroll | Dev 4 (Payroll) | T34 | 13-Sep (D12) | Should
2 | HRIS Operation - HR Policy Management | Policy library, versioning, publication, employee acknowledgement tracking | Tech Lead | T25 | 07-Sep (D8) | Should
2 | HRIS Operation - HR Reports & Analytics | Reporting framework, HR dashboard, standard report pack, Excel/PDF export | Tech Lead | T26 | 10-Sep (D11) | Should
2 | HRIS Operation - Promotion & Increment | Proposal, approval, grade/salary effect, effective-dated history | Dev 2 (Lifecycle) | T29 | 07-Sep (D8) | Must
3 | Payroll & Compensation & Benefits | Pay structure & formula engine, salary assignment, tax config, monthly run, payslip, bank advice, register | Dev 4 (Payroll) | T15, T16, T32, T33 | 10-Sep (D11) | Must
4 | Recruitment / ATS | Requisition & approval, job posting, career page, applicant pipeline, interview & scoring, offer | Dev 5 (Talent) | T17, T18 | 03-Sep (D6) | Should
5 | Benefits Management (PF / Gratuity) | PF contribution, ledger, interest, loan/withdrawal; gratuity accrual & calculation; final settlement | Dev 4 (Payroll) | T35, T36 | 15-Sep (D14) | Should
6 | HR Request & Approval | Generic multi-level workflow engine, delegation, escalation, SLA, request catalogue, approval inbox | Dev 1 (Platform) | T11, T12 | 03-Sep (D6) | Must
7 | HR Letters & Certificates | Templates with merge fields, auto-numbering, approval, PDF generation, issue register | Dev 5 (Talent) | T37 | 07-Sep (D8) | Should
8 | HR Asset Assignment | Asset register, issue/return/transfer, acknowledgement, employee-wise asset ledger | Dev 5 (Talent) | T38 | 08-Sep (D9) | Should
9 | Training & Development | Training plan & calendar, nomination, attendance, evaluation, cost & effectiveness tracking | Dev 5 (Talent) | T39 | 10-Sep (D11) | Could
10 | Employee Document Management | Document types, upload & versioning, expiry alerts, bulk upload, employee dossier | Dev 2 (Lifecycle) | T30 | 09-Sep (D10) | Should
11 | Performance Management | KPI/goal setting, appraisal cycle, self & manager review, rating, calibration, PIP | Dev 5 (Talent) | T40 | 14-Sep (D13) | Could
12 | Employee Self-Service (ESS) | Profile, attendance, leave apply, payslip, request submission, letters, document view | Dev 1 (Platform) | T41 | 14-Sep (D13) | Should
13 | Employee Exit / Separation | Resignation, notice period, clearance checklist, exit interview, certificate, final settlement | Dev 2 (Lifecycle) | T31, T36 | 15-Sep (D14) | Should
14 | Security & Administration (User Control / LOG) | Role/user/employee access management, menu & field permission matrix, audit log, activity trail | Dev 1 (Platform) | T27, T28 | 09-Sep (D10) | Must

## Milestones & Gates
MILESTONES, GATES & EXIT CRITERIA
Each gate must be signed off before the next wave is declared started.
ID | Date | Milestone | Exit criteria / definition of done | Owner | Status
M1 | 2026-09-03 | Foundation Freeze | Admin/Config, Employee Master, Approval Engine & Payroll config demo-ready | Tech Lead | Not reached
M2 | 2026-09-08 | Payroll Dry-Run | First monthly payroll executed on live attendance/leave data | Dev 4 (Payroll) | Not reached
M3 | 2026-09-10 | Feature Complete (Must) | All Must-tier modules code-complete; feature freeze begins | Tech Lead | Not reached
M4 | 2026-09-14 | UAT Build Deployed | Regression cycle 2 pass rate >= 95%; UAT environment live | QA / BA | Not reached
M5 | 2026-09-15 | Internal Demo & Go/No-Go | All 14 modules demonstrated; UAT hand-over pack signed | All | Not reached

## Risks & De-scope
RISK REGISTER & DE-SCOPE LADDER
If the plan slips, drop scope from the bottom of the de-scope ladder first - never compress QA.
# | Risk / Constraint | Impact | Likelihood | Mitigation | Owner
R1 | Only 14 working days for 14 modules (Fri/Sat are non-working) - the single largest constraint | High | High | Fixed scope tiers (Must/Should/Could). Could-tier features move to Phase 2 rather than slipping the date. | Tech Lead
R2 | Payroll depends on Attendance + Leave being stable; any slip in Dev 3 cascades into Dev 4 | High | High | Dry-run payroll on 08-Sep (M2) with partial attendance data; contract the interface on Day 2. | Dev 4 (Payroll)
R3 | Schema churn after ERD freeze forces rework across all tracks | High | Medium | Hard freeze on 30-Aug (D2). Any change after that needs Tech Lead approval and a written impact note. | Tech Lead
R4 | Attendance device (biometric/RFID) integration blocked by hardware or API access | High | Medium | Build against a mock device feed from Day 1; confirm real device API by 31-Aug or run file-import fallback. | Dev 3 (Time)
R5 | Performance Management and Training land in the last 4 days with no buffer | Medium | High | Explicitly Could-tier. Deliver configuration + core cycle only; advanced calibration/PIP in Phase 2. | Dev 5 (Talent)
R6 | Defects found in end-to-end testing (12-14 Sep) with only 1 fix day left | High | High | Feature freeze from 10-Sep (M3). Only P1/P2 defects fixed after 14-Sep; P3+ logged for Phase 2. | QA / BA
R7 | Statutory rules (income tax slab, PF/gratuity formula, labour law leave rules) not confirmed by business | High | Medium | Escalate for written confirmation by 31-Aug. Build formulas as configurable parameters, never hard-coded. | Dev 4 (Payroll)
R8 | Single QA resource across 14 modules becomes a bottleneck from 08-Sep | Medium | High | Developers own unit tests; QA focuses on integration & end-to-end. Add a second tester from 09-Sep if available. | QA / BA
R9 | Public holiday or leave inside the window reduces available days further | Medium | Medium | Confirm the holiday calendar on Day 1 and re-baseline the Gantt immediately if a day is lost. | Tech Lead
R10 | Reports & Analytics scope expands once users see the dashboard | Medium | High | Freeze the standard report list at kick-off (max 15 reports). Everything else is a Phase-2 change request. | Tech Lead
DE-SCOPE LADDER - if the 15 Sep date is at risk, cut in this order (top item cut first)
1 | Performance Management - calibration, PIP and 360-degree feedback (keep goal setting + basic appraisal)
2 | Training & Development - evaluation and cost/effectiveness tracking (keep plan, calendar, nomination)
3 | HR Reports & Analytics - anything beyond the 15 agreed standard reports and one dashboard
4 | Recruitment / ATS - public career page and candidate self-registration (keep internal requisition to offer)
5 | Benefits - PF loan and withdrawal workflow (keep contribution, ledger and gratuity calculation)
6 | ESS - document view and letter download (keep profile, attendance, leave, payslip)
7 | IOM - archive and full-text search (keep drafting, routing and acknowledgement)

## Calendar
WORKING CALENDAR
Working week = Sunday-Thursday. Friday & Saturday are non-working days.
Day # | Date | Weekday | Wave
D1 | 2026-08-27 | Thursday | Wave 0-1 : Foundation
D2 | 2026-08-30 | Sunday | Wave 0-1 : Foundation
D3 | 2026-08-31 | Monday | Wave 0-1 : Foundation
D4 | 2026-09-01 | Tuesday | Wave 0-1 : Foundation
D5 | 2026-09-02 | Wednesday | Wave 0-1 : Foundation
D6 | 2026-09-03 | Thursday | Wave 0-1 : Foundation
D7 | 2026-09-06 | Sunday | Wave 2 : Core Operations
D8 | 2026-09-07 | Monday | Wave 2 : Core Operations
D9 | 2026-09-08 | Tuesday | Wave 2 : Core Operations
D10 | 2026-09-09 | Wednesday | Wave 2 : Core Operations
D11 | 2026-09-10 | Thursday | Wave 2 : Core Operations
D12 | 2026-09-13 | Sunday | Wave 3 : Integration & UAT
D13 | 2026-09-14 | Monday | Wave 3 : Integration & UAT
D14 | 2026-09-15 | Tuesday | Wave 3 : Integration & UAT
Total working days | 14